## NCR 1
CHAKRADHARA AEROSPACE AND CARGO PRIVATE LIMITED QUALITY CONTROL DEPARTMENT
|  | NON CONFORMITY REPORT | [9 empty] | Work Centre : CACPL | [6 empty] | Date : 27.01.2021.
PROJECT : LTIV.OHPR & UTIV PARTS |  |  |  | PART NAME : INLET BELLOW END-2 | [6 empty] | DRG.No: 12CUS-6116-54-A,Rev:02,ISSUE:-
Po No : LPSC/LVF/2018E026730101 DT:12.12.2018. | [6 empty] | ASSY NAME : - |  |  |  | MATL. SPEC : SS 12X18 H10T |  |  |  | Stage: BEFORE PASSIVATION |  |  | NCR NO: C-NC / 21 / 033
Offered Qty :34No's |  |  | Ncr Qty: 34 No's |  |  | NCR Part Idn Nos : LA8491 To LA84934 |  |  |  |  | RMC NO: XSR/1030-46 |  |  |  | Matl Used: AISI 321 (SS 12X18H10T) |  |  | Report No: C-IR / 21 / 092
Sl. No | Dim sl. no. | Specification in MM |  |  | Tol. | DRG. ZONE | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 2 | 7 |  |  | +0.20/-0 | D8 | 6.97 | 6.98 | 6.97 | 6.98 | 6.96 | 6.98 | 6.98 | 6.96 | 6.98 | 6.96 | 6.97 | 6.98 | 6.97 | 6.98 | 6.97 | 6.96
6.99
[7 empty] | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[7 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[7 empty] | 6.98 | 6.97 | 6.97 | 6.98 | 6.97 | 6.98 | 6.97 | 6.99 | 6.98 | 6.97 | 6.97 | 6.98 | 6.97 | 6.96 | 6.97
[7 empty] | LA849 | LA849 | LA849 | LA849
[7 empty] | 31 | 32 | 33 | 34
[7 empty] | 6.96 | 6.97 | 6.96 | 6.97
Sl. No | Dim sl. no. | Specification in MM |  |  | Tol. | DRG. ZONE | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[7 empty] | 1 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 18 | 19
2 | 5 | Ø20.4 TH *** (Left) |  |  | - | E7 | 19.024 | 18.996 | 18.986 | 18.945 | 18.966 | 18.976 | 18.974 | 18.94 | 19.001 | 18.982 | 18.97 | 18.951 | 18.99 | 18.961 | 18.996 | 18.935
[7 empty] | 19.027 | 19 | 18.991 | 18.947 | 18.967 | 18.979 | 18.979 | 18.944 | 19.002 | 18.983 | 18.973 | 18.953 | 18.991 | 18.964 | 19.001 | 19.027
|  | Ø20.4 TH *** (Right) |  |  |  |  | 19.021 | 18.977 | 18.973 | 18.939 | 18.96 | 18.966 | 18.972 | 18.94 | 18.986 | 18.959 | 18.968 | 18.949 | 18.987 | 18.954 | 18.972
[7 empty] | 19.024 | 18.979 | 18.974 | 18.941 | 18.962 | 18.969 | 18.976 | 18.944 | 18.987 | 18.96 | 18.97 | 18.95 | 18.989 | 18.958 | 18.98
[7 empty] | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[7 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
[7 empty] | 18.998 | 18.953 | 18.972 | 18.99 | 19.025 | 18.987 | 18.946 | 18.955 | 18.955 | 19.002 | 18.987 | 18.98 | 18.96 | 19.004 | 18.981
[7 empty] | 19.003 | 18.969 | 18.974 | 18.993 | 19.027 | 18.988 | 18.948 | 18.956 | 18.958 | 19.006 | 18.988 | 18.982 | 18.963 | 19.005 | 18.984
[7 empty] | 18.984 | 18.945 | 18.965 | 18.986 | 19.022 | 18.982 | 18.935 | 18.958 | 18.947 | 18.987 | 18.975 | 18.973 | 18.953 | 18.976 | 18.975
[7 empty] | 18.989 | 18.962 | 18.968 | 18.989 | 19.024 | 18.983 | 18.937 | 18.959 | 18.95 | 18.992 | 18.976 | 18.975 | 18.954 | 18.978 | 18.972
Sl. No | Dim sl. no. | Specification in MM |  |  | Tol. | DRG. ZONE | 20: LA8491 To LA84934
3 | 56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference |  |  |  | E7 | 20: MAIN BODY S/A SUITING NOT DONE. GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING
Prepared By : | [6 empty] | 25: Verified By :
$

## INFPR 11-25
PART NAME : INLET BELLOW END-2 |  |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:- |  |  |  |  | Po No :LPSC/LVF/2018E026730101 DT:12.12.2018. |  |  |  | Report No:
SL No | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.ID | Remarks/ sign | Min | Max
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
1 | 37 | +0.20/-0.20 | [17 empty] | 36.8 | 37.2
[20 empty] | 36.8 | 37.2
2 | 7 | +0.20/-0 | [17 empty] | 7 | 7.2
[20 empty] | 7 | 7.2
3 | ⊥ 0.03 B ** | - | [17 empty] | - | -
[20 empty] | - | -
4 | 2 | - | [17 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
5 | Ø20.4 TH *** (Left) | - | [17 empty] | - | -
[20 empty] | - | -
5 | Ø20.4 TH *** (Right) | - | [17 empty] | - | -
[20 empty] | - | -
6 | 0.8√ On Ø20.4 | - | [17 empty] | - | -
[20 empty] | - | -
7 | Ø54 | +0.050/-0.050 | [17 empty] | 53.95 | 54.05
[20 empty] | 53.95 | 54.05
8 | 48 | +0/-0.250 | [17 empty] | 47.75 | 48
[20 empty] | 47.75 | 48
9 | M42X1.5-6H | - | [17 empty] | - | -
[20 empty] | - | -
9A | 40.376/40.676 | - | [17 empty] | - | -
[20 empty] | - | -
10 | ⊥ 0.03 B | - | [17 empty] | - | -
[20 empty] | - | -
11 | 1.5X45° | - | [17 empty] | - | -
[20 empty] | - | -
12 | RKeep sharp on Ø54 | - | [17 empty] | - | -
[20 empty] | - | -
13 | ⊚ 0.050 B ** On M42 | - | [17 empty] | - | -
[20 empty] | - | -
14 | 15° @-2-Places | - | [17 empty] | - | -
[20 empty] | - | -
15 | 4 | - | [17 empty] | 3.9 | 4.1
[20 empty] | 3.9 | 4.1
Inspected By |  |  | 12: Verified By:; 18: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.Id | Remarks
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
16 | 1 | - | [17 empty] | 0.9 | 1.1
[20 empty] | 0.9 | 1.1
17 | ⊥ 0.030 B | - | [17 empty] | - | -
[20 empty] | - | -
18 | ⊥ 0.030 B | - | [17 empty] | - | -
[20 empty] | - | -
19 | (11) | - | [17 empty] | - | -
[20 empty] | - | -
20 | 26 | +0.10/-0.10 | [17 empty] | 25.9 | 26.1
[20 empty] | 25.9 | 26.1
21 | 20 | - | [17 empty] | 19.8 | 20.2
[20 empty] | 19.8 | 20.2
22 | 2 | +0.250/-0 | [17 empty] | 2 | 2.25
[20 empty] | 2 | 2.25
23 | RKeep sharp on Ø20.4 | - | [17 empty] | - | -
[20 empty] | - | -
24 | M36X1.5-6g | - | [17 empty] | - | -
[20 empty] | - | -
24A | 35.968/35.732 | - | [17 empty] | - | -
[20 empty] | - | -
25 | ⊚Ø 0.050 B ** On M36 | - | [17 empty] | - | -
[20 empty] | - | -
26 | 25 | +0.21/-0 | [17 empty] | 25 | 25.21
[20 empty] | 25 | 25.21
27 | 22.4 | +0/-0.13 | [17 empty] | 22.27 | 22.4
[20 empty] | 22.27 | 22.4
28 | 1.5X45° | - | [17 empty] | - | -
[20 empty] | - | -
29 | 0.8√ On face | - | [17 empty] | - | -
[20 empty] | - | -
30 | 14 | - | [17 empty] | 13.8 | 14.2
[20 empty] | 13.8 | 14.2
Inspected By |  |  | 12: Verified By:; 18: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.Id | Remarks
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
31 | 2 | - | [17 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
32 | Ø54 | +0/-0.30 | [17 empty] | 53.7 | 54
[20 empty] | 53.7 | 54
33 | 1.5@ 3-Nos | +0.25/-0 | [17 empty] | 1.53 | 1.78
[20 empty] | 1.53 | 1.78
34 | Equispaced on Ø1.5 Hole | - | [17 empty] | - | -
[20 empty] | - | -
35 | 50 | +0/-0.30 | [17 empty] | 49.7 | 50
[20 empty] | 49.7 | 50
36 | 33.8 | 0/-0.25 | [17 empty] | 33.55 | 33.8
[20 empty] | 33.55 | 33.8
37 | 2.5 | - | [17 empty] | 2.4 | 2.6
[20 empty] | 2.4 | 2.6
38 | R1 *@ 2 Places | - | [17 empty] | - | -
[20 empty] | - | -
39 | 45° * | - | [17 empty] | - | -
[20 empty] | - | -
40 | R0.5 * | - | [17 empty] | 0.4 | 0.6
[20 empty] | 0.4 | 0.6
41 | R2 * | - | [17 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
42 | Ø30 | +0.21/-0 | [17 empty] | 30 | 30.21
[20 empty] | 30 | 30.21
43 | 3 * | - | [17 empty] | 2.9 | 3.1
[20 empty] | 2.9 | 3.1
44 | 45° * | - | [17 empty] | - | -
[20 empty] | - | -
45 | R0.5 * | - | [17 empty] | - | -
[20 empty] | - | -
46 | R1 * | - | [17 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 12: Verified By:; 18: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.Id | Remarks
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
47 | 42.5 | +0.250/-0 | [17 empty] | 42.5 | 42.75
[20 empty] | 42.5 | 42.75
48 | 0.8√ On Groove face | - | [17 empty] | - | -
[20 empty] | - | -
49 | Ensure the matrial is annealed condition | - | [17 empty] | - | -
[20 empty] | - | -
50 | * Dimensions to be ensured by machining tools previously inspected | - | [17 empty] | - | -
[20 empty] | - | -
51 | ** Dimension to be ensured by machining process | - | [17 empty] | - | -
[20 empty] | - | -
52 | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference | - | [17 empty] | - | -
[20 empty] | - | -
53 | Passivation | - | [17 empty] | - | -
[20 empty] | - | -
54 | Thread should be free from burrs end folding,chatering marks etc | - | [17 empty] | - | -
[20 empty] | - | -
55 | By using TAG | - | [17 empty] | - | -
[20 empty] | - | -
56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference | - | [17 empty] | - | -
[20 empty] | - | -
57 | 3.2√ | - | [17 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 12: Verified By:; 18: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
1 | 37 | +0.20/-0.20 | [17 empty] | 36.8 | 37.2
[20 empty] | 36.8 | 37.2
2 | 7 | +0.20/-0 | [17 empty] | 7 | 7.2
[20 empty] | 7 | 7.2
3 | ⊥ 0.03 B ** | - | [17 empty] | - | -
[20 empty] | - | -
4 | 2 | - | [17 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
5 | Ø20.4 TH *** (Left) | - | [17 empty] | - | -
[20 empty] | - | -
5 | Ø20.4 TH *** (Right) | - | [17 empty] | - | -
[20 empty] | - | -
6 | 0.8√ On Ø20.4 | - | [17 empty] | - | -
[20 empty] | - | -
7 | Ø54 | +0.050/-0.050 | [17 empty] | 53.95 | 54.05
[20 empty] | 53.95 | 54.05
8 | 48 | +0/-0.250 | [17 empty] | 47.75 | 48
[20 empty] | 47.75 | 48
9 | M42X1.5-6H | - | [17 empty] | - | -
[20 empty] | - | -
9A | 40.376/40.676 | - | [17 empty] | - | -
[20 empty] | - | -
10 | ⊥ 0.03 B | - | [17 empty] | - | -
[20 empty] | - | -
11 | 1.5X45° | - | [17 empty] | - | -
[20 empty] | - | -
12 | RKeep sharp on Ø54 | - | [17 empty] | - | -
[20 empty] | - | -
13 | ⊚ 0.050 B ** On M42 | - | [17 empty] | - | -
[20 empty] | - | -
14 | 15° @-2-Places | - | [17 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
15 | 4 | - | [17 empty] | 3.9 | 4.1
[20 empty] | 3.9 | 4.1
16 | 1 | - | [17 empty] | 0.9 | 1.1
[20 empty] | 0.9 | 1.1
17 | ⊥ 0.030 B | - | [17 empty] | - | -
[20 empty] | - | -
18 | ⊥ 0.030 B | - | [17 empty] | - | -
[20 empty] | - | -
19 | (11) | - | [17 empty] | - | -
[20 empty] | - | -
20 | 26 | +0.10/-0.10 | [17 empty] | 25.9 | 26.1
[20 empty] | 25.9 | 26.1
21 | 20 | - | [17 empty] | 19.8 | 20.2
[20 empty] | 19.8 | 20.2
22 | 2 | +0.250/-0 | [17 empty] | 2 | 2.25
[20 empty] | 2 | 2.25
23 | RKeep sharp on Ø20.4 | - | [17 empty] | - | -
[20 empty] | - | -
24 | M36X1.5-6g | - | [17 empty] | - | -
[20 empty] | - | -
24A | 35.968/35.732 | - | [17 empty] | - | -
[20 empty] | - | -
25 | ⊚Ø 0.050 B ** On M36 | - | [17 empty] | - | -
[20 empty] | - | -
26 | 25 | +0.21/-0 | [17 empty] | 25 | 25.21
[20 empty] | 25 | 25.21
27 | 22.4 | +0/-0.13 | [17 empty] | 22.27 | 22.4
[20 empty] | 22.27 | 22.4
28 | 1.5X45° | - | [17 empty] | - | -
[20 empty] | - | -
29 | 0.8√ On face | - | [17 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
30 | 14 | - | [17 empty] | 13.8 | 14.2
[20 empty] | 13.8 | 14.2
31 | 2 | - | [17 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
32 | Ø54 | +0/-0.30 | [17 empty] | 53.7 | 54
[20 empty] | 53.7 | 54
33 | 1.5@ 3-Nos | +0.25/-0 | [17 empty] | 1.53 | 1.78
[20 empty] | 1.53 | 1.78
34 | Equispaced on Ø1.5 Hole | - | [17 empty] | - | -
[20 empty] | - | -
35 | 50 | +0/-0.30 | [17 empty] | 49.7 | 50
[20 empty] | 49.7 | 50
36 | 33.8 | 0/-0.25 | [17 empty] | 33.55 | 33.8
[20 empty] | 33.55 | 33.8
37 | 2.5 | - | [17 empty] | 2.4 | 2.6
[20 empty] | 2.4 | 2.6
38 | R1 *@ 2 Places | - | [17 empty] | - | -
[20 empty] | - | -
39 | 45° * | - | [17 empty] | - | -
[20 empty] | - | -
40 | R0.5 * | - | [17 empty] | 0.4 | 0.6
[20 empty] | 0.4 | 0.6
41 | R2 * | - | [17 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
42 | Ø30 | +0.21/-0 | [17 empty] | 30 | 30.21
[20 empty] | 30 | 30.21
43 | 3 * | - | [17 empty] | 2.9 | 3.1
[20 empty] | 2.9 | 3.1
44 | 45° * | - | [17 empty] | - | -
[20 empty] | - | -
45 | R0.5 * | - | [17 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
46 | R1 * | - | [17 empty] | - | -
[20 empty] | - | -
47 | 42.5 | +0.250/-0 | [17 empty] | 42.5 | 42.75
[20 empty] | 42.5 | 42.75
48 | 0.8√ On Groove face | - | [17 empty] | - | -
[20 empty] | - | -
49 | Ensure the matrial is annealed condition | - | [17 empty] | - | -
[20 empty] | - | -
50 | * Dimensions to be ensured by machining tools previously inspected | - | [17 empty] | - | -
[20 empty] | - | -
51 | ** Dimension to be ensured by machining process | - | [17 empty] | - | -
[20 empty] | - | -
52 | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference | - | [17 empty] | - | -
[20 empty] | - | -
53 | Passivation | - | [17 empty] | - | -
[20 empty] | - | -
54 | Thread should be free from burrs end folding,chatering marks etc | - | [17 empty] | - | -
[20 empty] | - | -
55 | By using TAG | - | [17 empty] | - | -
[20 empty] | - | -
56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference | - | [17 empty] | - | -
[20 empty] | - | -
57 | 3.2√ | - | [17 empty] | - | -
[20 empty] | - | -
Slno | NOTES |  | 27: COMMENTS
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor | [10 empty] | $
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor

## QP
CHAKRADHARA AEROSPACE AND CARGO PRIVATE LIMITED
QUALITY ASSURANCE DEPARTMENT
QUALITY PLAN FOR FINAL INSPECTION
PROJECT : |  | LTIV.OHPR & UTIV PARTS |  |  | QP No. : | -
PART NAME : |  | INLET BELLOW END-2 |  |  | QP REV No. : | 1.0
DRG No. |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:- |  |  | MATL. SPEC : | SS 12X18 H10T
ASSY NAME : |  | - |  |  | SAMPLING PLAN : | 100%
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
1 | Total length | 37 | +0.20/-0.20 | D7 | DHMS |  | 0.001 | - | - | - | 2
2 | Distance | 7 | +0.20/-0 | D8 | DHMS |  | 0.001 | - | - | - | 2
3 | Perpendicularity | ⊥ 0.03 B ** | - | D8 | CMM |  | 0.1㎛ | - | - | - | 2
4 | Distance | 2 | - | D8 | Video measuring system |  | 0.001 | - | +0.1 | -0.1 | 2
5 | Inner diameter | Ø20.4 TH *** (Left) | - | E7 | CMM |  | 0.1㎛ | - | - | - | 2
5 | Inner diameter | Ø20.4 TH *** (Right) | - | E7 | CMM |  | 0.1㎛ | - | - | - | 2
6 | Surface finish | 0.8√ On Ø20.4 | - | E8 | Roughness Tester |  | 0.01㎛ | - | - | - | 2
7 | Outer diameter | Ø54 | +0.050/-0.050 | E8 | Digital micrometer |  | 0.001 | - | - | - | 2
8 | Groove diameter (Internal groove) | 48 | +0/-0.250 | E8 | Digital vernier |  | 0.01 | - | - | - | 2
9 | Internal thread | M42X1.5-6H | - | E8 | Thread plug gauge Go and No go |  | N/A | - | - | - | 2
9A | Minor diameter of M42 | 40.376/40.676 | - | - | Digital vernier |  | 0.01 | - | - | - | 2
10 | Perpendicularity | ⊥ 0.03 B | - | E8 | CMM |  | 0.1㎛ | - | - | - | 2
11 | Chamfer | 1.5X45° | - | E8 | Contour measuring system |  | 0.001 | - | - | - | 2
12 | Keep sharp | RKeep sharp on Ø54 | - | E8 | Visual under 10X |  | N/A | - | - | - | 2
13 | Concentricity | ⊚ 0.050 B ** On M42 | - | F8 | CMM With cylinder probe |  | 0.1㎛ | - | - | - | 2
14 | Angle | 15° @-2-Places | - | F7 | Video measuring system |  | 0.001 | - | - | - | 2
15 | Hole distance | 4 | - | F7 | DHMS |  | 0.001 | - | +0.1 | -0.1 | 2
16 | Chamfer length | 1 | - | F7 | Video measuring system |  | 0.001 | - | +0.1 | -0.1 | 2
17 | Perpendicularity | ⊥ 0.030 B | - | F6 | CMM |  | 0.1㎛ | - | - | - | 2
18 | Perpendicularity | ⊥ 0.030 B | - | F6 | CMM |  | 0.1㎛ | - | - | - | 2
19 | Depth | (11) | - | F6 | DHMS |  | 0.001 | - | - | - | 2
Prepared By : |  | Vijayan | Verified By : |  | Vijayan | Approved By : | Vijayan
Date : |  | 12/23/2020 | Date : |  |  | Date :
PART NAME: INLET BELLOW END-2 |  |  |  |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:-
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
20 | Depth | 26 | +0.10/-0.10 | E7 | DHMS |  | 0.001 | - | - | - | 2
21 | Depth | 20 | - | E7 | DHMS |  | 0.001 | - | +0.2 | -0.2 | 2
22 | Depth | 2 | +0.250/-0 | E6 | DHMS |  | 0.001 | - | - | - | 2
23 | Keep sharp | RKeep sharp on Ø20.4 | - | E6 | Visual under 10X |  | N/A | - | - | - | 2
24 | External thread | M36X1.5-6g | - | E6 | Thread Ring gauge Go and No go |  | N/A | - | - | - | 2
24A | Major diameter of M36 | 35.968/35.732 | - | E6 | Digital vernier |  | 0.01 | - | - | - | 2
25 | Concentricity | ⊚Ø 0.050 B ** On M36 | - | E | CMM With cylinder probe |  | 0.1㎛ | - | - | - | 2
26 | Groove diameter (Internal groove) | 25 | +0.21/-0 | E6 | DHMS |  | 0.001 | - | - | - | 2
27 | Groove diameter (Outer groove) | 22.4 | +0/-0.13 | E6 | DHMS |  | 0.001 | - | - | - | 2
28 | Chamfer | 1.5X45° | - | D6 | Video measuring system |  | 0.001 | - | - | - | 2
29 | Surface finish | 0.8√ On face | - | D6 | Compare with measured sample |  | N/A | - | - | - | 2
30 | Depth | 14 | - | D6 | DHMS |  | 0.001 | - | +0.2 | -0.2 | 2
31 | Hole distance | 2 | - | E4 | Measuring pin with Video measuring system |  | 0.001 | - | +0.1 | -0.1 | 2
32 | Outer diameter | Ø54 | +0/-0.30 | E3 | Digital vernier |  | 0.01 | - | - | - | 2
33 | Hole diameter | 1.5@ 3-Nos | +0.25/-0 | D3 | Measuring pin 1.51 No go 1.74 |  | N/A | - | - | - | 2
34 | Equispaced | Equispaced on Ø1.5 Hole | - | D3 | Measuring pin with Video measuring system |  | 0.001 | - | - | - | 2
35 | Distance | 50 | +0/-0.30 | C4 | DHMS |  | 0.001 | - | - | - | 2
36 | Groove diameter (Outer groove) | 33.8 | 0/-0.25 | B5 | DHMS/Video measuring system |  | 0.001 | - | - | - | 2
37 | Groove width | 2.5 | - | C5 | Video measuring system |  | 0.001 | - | +0.1 | -0.1 | 2
38 | Radius | R1 *@ 2 Places | - | C4 | Radius gauge |  | N/A | - | - | - | 2
39 | Angle | 45° * | - | C4 | Video measuring system |  | 0.001 | - | - | - | 2
40 | Radius | R0.5 * | - | B4 | Radius gauge |  | N/A | - | +0.1 | -0.1 | 2
41 | Radius | R2 * | - | B4 | Radius gauge |  | N/A | - | +0.1 | -0.1 | 2
42 | Inner diameter | Ø30 | +0.21/-0 | B4 | Bore micrometer |  | 0.001 | - | - | - | 2
43 | Groove width | 3 * | - | B7 | Contour measuring system |  | 0.001 | - | +0.1 | -0.1 | 2
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
44 | Angle | 45° * | - | B7 | Contour measuring system |  | 0.001 | - | - | - | 2
45 | Radius | R0.5 * | - | C7 | Radius gauge |  | N/A | - | - | - | 2
46 | Radius | R1 * | - | C6 | Radius gauge |  | N/A | - | - | - | 2
47 | Groove diameter (Internal groove) | 42.5 | +0.250/-0 | B6 | DHMS |  | 0.001 | - | - | - | 2
48 | Surface finish | 0.8√ On Groove face | - | B6 | Compare with Std specimen |  | N/A | - | - | - | 2
49 | - | Ensure the matrial is annealed condition | - | - | Verify the HT report as per procedure |  | N/A | - | - | - | 2
50 | - | * Dimensions to be ensured by machining tools previously inspected | - | - | - |  | N/A | - | - | - | 2
51 | - | ** Dimension to be ensured by machining process | - | - | - |  | N/A | - | - | - | 2
52 | - | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference | - | - | Ensure the suiting list |  | N/A | - | - | - | 2
53 | Protection | Passivation | - | - | Verify the report as per procedure |  | N/A | - | - | - | 2
54 | - | Thread should be free from burrs end folding,chatering marks etc | - | - | Visual under 10X |  | N/A | - | - | - | 2
55 | Identification Nos | By using TAG | - | - | Visual |  | N/A | - | - | - | 2
56 | - | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference | - | - | Ensure the suiting list |  | N/A | - | - | - | 2
57 | General surface finish | 3.2√ | - | - | - |  | - | - | - | - | 2
Slno | NOTES |  |  |  | COMMENTS
Prepared By : |  | Vijayan | Verified By : |  | Vijayan | Approved By : | Vijayan
Date : |  | 12/23/2020 | Date : |  |  | Date : |  |  |  |  | $
PART NAME: INLET BELLOW END-2 |  |  |  |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:-
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :
SL No | Parameters | Specification in MM | Tol. | Drg. Zone | Instruments / Gauges used |  | Least Count | Remarks | TOL(+) | TOL(-)
Prepared By : |  |  | Verified By : |  |  | Approved By :
Date : |  |  | Date : |  |  | Date :

## INFPR
CHAKRADHARA AEROSPACE AND CARGO PRIVATE LIMITED | [18 empty] | L
QUALITY CONTROL DEPARTMENT | [14 empty] | Wo No:2010521
PROJECT : LTIV.OHPR & UTIV PARTS |  |  | PART NAME : INLET BELLOW END-2 | [5 empty] | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:- | [5 empty] | FIR No:
Po No :LPSC/LVF/2018E026730101 DT:12.12.2018. |  |  | ASSY NAME : - |  | MATL. SPEC : SS 12X18 H10T |  |  |  | Stage: BEFORE PASSIVATION |  |  | Report No: |  |  | Date:
Offered Qty :34No's |  |  | PART ID NO's LA8491ToLA84934 |  | RMC NO: XSR/1030-46 |  |  |  | Matl Used: AISI 321 (SS 12X18H10T) |  |  | NCR NO: |  |  | B.Qty:
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.ID: | Remarks | Min | Max
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 37 | +0.20/-0.20 | DHMS | 0.001 | [12 empty] | 36.8 | 37.2
[17 empty] | 36.8 | 37.2
2 | 7 | +0.20/-0 | DHMS | 0.001 | [12 empty] | 7 | 7.2
[17 empty] | 7 | 7.2
3 | ⊥ 0.03 B ** | - | CMM | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
4 | 2 | - | Video measuring system | 0.001 | [12 empty] | 1.9 | 2.1
[17 empty] | 1.9 | 2.1
5 | Ø20.4 TH *** (Left) | - | CMM | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
5 | Ø20.4 TH *** (Right) | - | CMM | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
6 | 0.8√ On Ø20.4 | - | Roughness Tester | 0.01㎛ | [12 empty] | - | -
[17 empty] | - | -
7 | Ø54 | +0.050/-0.050 | Digital micrometer | 0.001 | [12 empty] | 53.95 | 54.05
[17 empty] | 53.95 | 54.05
8 | 48 | +0/-0.250 | Digital vernier | 0.01 | [12 empty] | 47.75 | 48
[17 empty] | 47.75 | 48
9 | M42X1.5-6H | - | Thread plug gauge Go and No go | N/A | [12 empty] | - | -
[17 empty] | - | -
9A | 40.376/40.676 | - | Digital vernier | 0.01 | [12 empty] | - | -
[17 empty] | - | -
CACPL |  |  |  |  | 2: CUSTOMER SURVEYOR
Inspected By: |  |  | Sign & Stamp |  | 2: Qty Accepted; 5: Qty Concession; 8: Qty Rejected
Verified By: |  |  | Sign & Stamp |  | 2: Name & Signature :
DATE: |  |  | DATE: |  | 2: Date :
PART NAME : INLET BELLOW END-2 |  |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:- |  | 1: Po No :LPSC/LVF/2018E026730101 DT:12.12.2018.; 5: Report No:
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.ID: | Remarks
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
10 | ⊥ 0.03 B | - | CMM | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
11 | 1.5X45° | - | Contour measuring system | 0.001 | [12 empty] | - | -
[17 empty] | - | -
12 | RKeep sharp on Ø54 | - | Visual under 10X | N/A | [12 empty] | - | -
[17 empty] | - | -
13 | ⊚ 0.050 B ** On M42 | - | CMM With cylinder probe | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
14 | 15° @-2-Places | - | Video measuring system | 0.001 | [12 empty] | - | -
[17 empty] | - | -
15 | 4 | - | DHMS | 0.001 | [12 empty] | 3.9 | 4.1
[17 empty] | 3.9 | 4.1
16 | 1 | - | Video measuring system | 0.001 | [12 empty] | 0.9 | 1.1
[17 empty] | 0.9 | 1.1
17 | ⊥ 0.030 B | - | CMM | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
18 | ⊥ 0.030 B | - | CMM | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
19 | (11) | - | DHMS | 0.001 | [12 empty] | - | -
[17 empty] | - | -
20 | 26 | +0.10/-0.10 | DHMS | 0.001 | [12 empty] | 25.9 | 26.1
[17 empty] | 25.9 | 26.1
21 | 20 | - | DHMS | 0.001 | [12 empty] | 19.8 | 20.2
[17 empty] | 19.8 | 20.2
22 | 2 | +0.250/-0 | DHMS | 0.001 | [12 empty] | 2 | 2.25
[17 empty] | 2 | 2.25
23 | RKeep sharp on Ø20.4 | - | Visual under 10X | N/A | [12 empty] | - | -
[17 empty] | - | -
24 | M36X1.5-6g | - | Thread Ring gauge Go and No go | N/A | [12 empty] | - | -
[17 empty] | - | -
24A | 35.968/35.732 | - | Digital vernier | 0.01 | [12 empty] | - | -
[17 empty] | - | -
25 | ⊚Ø 0.050 B ** On M36 | - | CMM With cylinder probe | 0.1㎛ | [12 empty] | - | -
[17 empty] | - | -
Inspected By : |  |  | Verified By: |  | 5: Report No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
26 | 25 | +0.21/-0 | DHMS | 0.001 | [12 empty] | 25 | 25.21
[17 empty] | 25 | 25.21
27 | 22.4 | +0/-0.13 | DHMS | 0.001 | [12 empty] | 22.27 | 22.4
[17 empty] | 22.27 | 22.4
28 | 1.5X45° | - | Video measuring system | 0.001 | [12 empty] | - | -
[17 empty] | - | -
29 | 0.8√ On face | - | Compare with measured sample | N/A | [12 empty] | - | -
[17 empty] | - | -
30 | 14 | - | DHMS | 0.001 | [12 empty] | 13.8 | 14.2
[17 empty] | 13.8 | 14.2
31 | 2 | - | Measuring pin with Video measuring system | 0.001 | [12 empty] | 1.9 | 2.1
[17 empty] | 1.9 | 2.1
32 | Ø54 | +0/-0.30 | Digital vernier | 0.01 | [12 empty] | 53.7 | 54
[17 empty] | 53.7 | 54
33 | 1.5@ 3-Nos | +0.25/-0 | Measuring pin 1.51 No go 1.74 | N/A | [12 empty] | 1.53 | 1.78
[17 empty] | 1.53 | 1.78
34 | Equispaced on Ø1.5 Hole | - | Measuring pin with Video measuring system | 0.001 | [12 empty] | - | -
[17 empty] | - | -
35 | 50 | +0/-0.30 | DHMS | 0.001 | [12 empty] | 49.7 | 50
[17 empty] | 49.7 | 50
36 | 33.8 | 0/-0.25 | DHMS/Video measuring system | 0.001 | [12 empty] | 33.55 | 33.8
[17 empty] | 33.55 | 33.8
37 | 2.5 | - | Video measuring system | 0.001 | [12 empty] | 2.4 | 2.6
[17 empty] | 2.4 | 2.6
38 | R1 *@ 2 Places | - | Radius gauge | N/A | [12 empty] | - | -
[17 empty] | - | -
39 | 45° * | - | Video measuring system | 0.001 | [12 empty] | - | -
[17 empty] | - | -
40 | R0.5 * | - | Radius gauge | N/A | [12 empty] | 0.4 | 0.6
[17 empty] | 0.4 | 0.6
41 | R2 * | - | Radius gauge | N/A | [12 empty] | 1.9 | 2.1
[17 empty] | 1.9 | 2.1
Inspected By : |  |  | Verified By: |  | 5: Report No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
42 | Ø30 | +0.21/-0 | Bore micrometer | 0.001 | [12 empty] | 30 | 30.21
[17 empty] | 30 | 30.21
43 | 3 * | - | Contour measuring system | 0.001 | [12 empty] | 2.9 | 3.1
[17 empty] | 2.9 | 3.1
44 | 45° * | - | Contour measuring system | 0.001 | [12 empty] | - | -
[17 empty] | - | -
45 | R0.5 * | - | Radius gauge | N/A | [12 empty] | - | -
[17 empty] | - | -
46 | R1 * | - | Radius gauge | N/A | [12 empty] | - | -
[17 empty] | - | -
47 | 42.5 | +0.250/-0 | DHMS | 0.001 | [12 empty] | 42.5 | 42.75
[17 empty] | 42.5 | 42.75
48 | 0.8√ On Groove face | - | Compare with Std specimen | N/A | [12 empty] | - | -
[17 empty] | - | -
49 | Ensure the matrial is annealed condition | - | Verify the HT report as per procedure | N/A | [12 empty] | - | -
[17 empty] | - | -
50 | * Dimensions to be ensured by machining tools previously inspected | - | - | N/A | [12 empty] | - | -
[17 empty] | - | -
51 | ** Dimension to be ensured by machining process | - | - | N/A | [12 empty] | - | -
[17 empty] | - | -
52 | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference | - | Ensure the suiting list | N/A | [12 empty] | - | -
[17 empty] | - | -
53 | Passivation | - | Verify the report as per procedure | N/A | [12 empty] | - | -
[17 empty] | - | -
54 | Thread should be free from burrs end folding,chatering marks etc | - | Visual under 10X | N/A | [12 empty] | - | -
[17 empty] | - | -
55 | By using TAG | - | Visual | N/A | [12 empty] | - | -
[17 empty] | - | -
56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference | - | Ensure the suiting list | N/A | [12 empty] | - | -
[17 empty] | - | -
57 | 3.2√ | - | - | - | [12 empty] | - | -
[17 empty] | - | -
Inspected By : |  |  | Verified By: |  | 5: Report No.; 8: NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count | [14 empty] | $
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[9 empty] | Report No. |  |  | NCR No.

## REPORT
CHAKRADHARA AEROSPACE AND CARGO PRIVATE LIMITED QUALITY CONTROL DEPARTMENT | [19 empty] | L
INSPECTION REPORT | [12 empty] | WO No : 2010521 |  |  | Wo No:2010521
PROJECT : LTIV.OHPR & UTIV PARTS |  |  | PART NAME : INLET BELLOW END-2 | [6 empty] | DRG.No: 12CUS-6116-54-A,Rev:02,ISSUE:- | [5 empty] | FIR No:
Po No : LPSC/LVF/2018E026730101 DT:12.12.2018. |  |  | ASSY NAME : - |  |  | MATL. SPEC : SS 12X18 H10T |  |  |  | Stage: BEFORE PASSIVATION |  |  | Report No: C-IR / 21 / 092 |  |  | Date:
Offered Qty :34No's |  |  | PART ID NO's : LA8491 To LA84934 |  |  | RMC NO: XSR/1030-46 |  |  |  | Matl Used: AISI 321 (SS 12X18H10T) |  |  | NCR NO: C-NC / 21 / 033 |  |  | B.Qty:
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.ID: | Remarks | Min | Max
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 37 | +0.20/-0.20 | DHMS |  | 0.001 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.02 | 37.03 | 37.02 |  |  | 36.8 | 37.2
[18 empty] | 36.8 | 37.2
2 | 7 | +0.20/-0 | DHMS |  | 0.001 | 6.97 | 6.98 | 6.97 | 6.98 | 6.96 | 6.98 | 6.98 | 6.96 | 6.98 | 6.96 |  |  | 7 | 7.2
[18 empty] | 7 | 7.2
3 | ⊥ 0.03 B ** | - | CMM |  | 0.1㎛ | 0.011 | 0.005 | 0.006 | 0.012 | 0.019 | 0.012 | 0.009 | 0.014 | 0.006 | 0.01 |  |  | 0 | 0.03
[18 empty] | 0 | 0.03
4 | 2 | - | Video measuring system |  | 0.001 | 2.08 | 2.1 | 2.08 | 2.1 | 2.09 | 2.07 | 2.08 | 2.07 | 2.09 | 2.1 |  |  | 1.9 | 2.1
[18 empty] | 1.9 | 2.1
5 | Ø20.4 TH *** (Left) | - | CMM |  | 0.1㎛ | 19.024 | 20.419 | 20.521 | 18.996 | 18.986 | 18.945 | 18.966 | 18.976 | 18.974 | 18.94 |  |  | 20.2 | 20.6
[6 empty] | 19.027 | 20.42 | 20.524 | 19 | 18.991 | 18.947 | 18.967 | 18.979 | 18.979 | 18.944 |  |  | 20.2 | 20.6
5A | Ø20.4 TH *** (Right) | - | CMM |  | 0.1㎛ | 19.021 | 20.431 | 20.54 | 18.977 | 18.973 | 18.939 | 18.96 | 18.966 | 18.972 | 18.94 |  |  | 20.2 | 20.6
[6 empty] | 19.024 | 20.432 | 20.542 | 18.979 | 18.974 | 18.941 | 18.962 | 18.969 | 18.976 | 18.944 |  |  | 20.2 | 20.6
6 | 0.8√ On Ø20.4 | - | Roughness Tester |  | 0.01㎛ | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 |  |  | 0 | 0.8
[18 empty] | 0 | 0.8
7 | Ø54 | +0.050/-0.050 | Digital micrometer |  | 0.001 | 54.02 | 54.03 | 54.03 | 54.02 | 54.03 | 54.03 | 54.02 | 54.03 | 54.02 | 54.03 |  |  | 53.95 | 54.05
[18 empty] | 53.95 | 54.05
8 | 48 | +0/-0.250 | Digital vernier |  | 0.01 | 47.9 | 47.91 | 47.89 | 47.9 | 47.89 | 47.9 | 47.91 | 47.92 | 47.91 | 47.92 |  |  | 47.75 | 48
[18 empty] | 47.75 | 48
9 | M42X1.5-6H **** | - | Thread plug gauge Go and No go |  | N/A | 1: GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING |  |  | - | -
[18 empty] | - | -
9A | 40.376/40.676 | - | Digital vernier |  | 0.01 | 40.49 | 40.55 | 40.56 | 40.54 | 40.56 | 40.54 | 40.56 | 40.56 | 40.55 | 40.56 |  |  | 40.376 | 40.676
[18 empty] | 40.376 | 40.676
CACPL | [5 empty] | 2: CUSTOMER SURVEYOR
Inspected By: S. MANOJ KUMAR |  |  | Sign & Stamp |  |  | 2: Qty Accepted; 5: Qty Concession; 8: Qty Rejected
Verified By: M. SARAVANAN |  |  | Sign & Stamp |  |  | 2: Name & Signature :
DATE: 24.12.2020. |  |  | DATE: |  |  | 2: Date :
PART NAME : INLET BELLOW END-2 |  |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:- |  |  | 1: Po No :LPSC/LVF/2018E026730101 DT:12.12.2018.; 8: Report No: C-IR / 21 / 092
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.ID: | Remarks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
10 | ⊥ 0.03 B | - | CMM |  | 0.1㎛ | 0.009 | 0.004 | 0.006 | 0.009 | 0.013 | 0.008 | 0.007 | 0.009 | 0.007 | 0.008 |  |  | 0 | 0.03
[18 empty] | 0 | 0.03
11 | 1.5X45° | - | Contour measuring system |  | 0.001 | 1: 1.5X45° PROVIDED |  |  | - | -
[18 empty] | - | -
12 | Keep sharp on Ø54 | - | Visual under 10X |  | N/A | 1: KEEP SHARP PROVIDED |  |  | - | -
[18 empty] | - | -
13 | ⊚ 0.050 B ** On M42 | - | CMM With cylinder probe |  | 0.1㎛ | 0.005 | 0.002 | 0.008 | 0.014 | 0.014 | 0.009 | 0.009 | 0.016 | 0.005 | 0.009 |  |  | 0 | 0.05
[18 empty] | 0 | 0.05
14 | 15° @-2-Places | - | Video measuring system |  | 0.001 | 1: MEASURED BETWEEN 14°56' TO 15°04' |  |  | - | -
[18 empty] | - | -
15 | 4 | - | DHMS |  | 0.001 | 3.95 | 3.96 | 3.95 | 3.96 | 3.95 | 3.96 | 3.95 | 3.96 | 3.95 | 3.96 |  |  | 3.9 | 4.1
[18 empty] | 3.9 | 4.1
16 | 1 | - | Video measuring system |  | 0.001 | 0.99 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 |  |  | 0.9 | 1.1
[18 empty] | 0.9 | 1.1
17 | ⊥ 0.030 B On 14mm Depth Face | - | CMM |  | 0.1㎛ | 0.01 | 0.013 | 0.015 | 0.022 | 0.021 | 0.01 | 0.006 | 0.005 | 0.01 | 0.007 |  |  | 0 | 0.03
[18 empty] | 0 | 0.03
18 | ⊥ 0.030 B On 11mm Depth Face | - | CMM |  | 0.1㎛ | 0.003 | 0.007 | 0.028 | 0.029 | 0.007 | 0.005 | 0.003 | 0.001 | 0.005 | 0.004 |  |  | 0 | 0.03
[18 empty] | 0 | 0.03
19 | (11) | - | DHMS |  | 0.001 | 11.02 | 11.01 | 11.04 | 11.02 | 11.04 | 11.02 | 11.04 | 11.02 | 11.04 | 11.02 |  |  | 10.8 | 11.2
[18 empty] | 10.8 | 11.2
20 | 26 | +0.10/-0.10 | DHMS |  | 0.001 | 25.98 | 25.97 | 26.01 | 26.02 | 26.01 | 25.99 | 26.01 | 26.02 | 26.01 | 26.02 |  |  | 25.9 | 26.1
[18 empty] | 25.9 | 26.1
21 | 20 | - | DHMS |  | 0.001 | 20.02 | 20.01 | 20.02 | 20.01 | 19.98 | 19.99 | 19.97 | 19.99 | 20.01 | 20 |  |  | 19.8 | 20.2
[18 empty] | 19.8 | 20.2
22 | 2 | +0.250/-0 | DHMS |  | 0.001 | 2.12 | 2.13 | 2.12 | 2.15 | 2.14 | 2.16 | 2.14 | 2.14 | 2.16 | 2.15 |  |  | 2 | 2.25
[18 empty] | 2 | 2.25
23 | Keep sharp on Ø20.4 | - | Visual under 10X |  | N/A | 1: KEEP SHARP PROVIDED |  |  | - | -
[18 empty] | - | -
24 | M36X1.5-6g | - | Thread Ring gauge Go and No go |  | N/A | 1: GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING |  |  | - | -
[18 empty] | - | -
24A | 35.968/35.732 | - | Digital vernier |  | 0.01 | 35.85 | 35.92 | 35.91 | 35.92 | 35.93 | 35.92 | 35.92 | 35.93 | 35.92 | 35.93 |  |  | 34 | 38
[18 empty] | 34 | 38
25 | ⊚Ø 0.050 B ** On M36 | - | CMM With cylinder probe |  | 0.1㎛ | 0.001 | 0.015 | 0.014 | 0.01 | 0.01 | 0.004 | 0.003 | 0.001 | 0.006 | 0.003 |  |  | 0 | 0.05
[18 empty] | 0 | 0.05
Inspected By |  |  |  | Verified By: |  | 5: Customer Surveyor :
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
26 | 25 | +0.21/-0 | DHMS |  | 0.001 | 25.14 | 25.16 | 25.14 | 25.12 | 25.12 | 25.13 | 25.14 | 25.12 | 25.13 | 25.12 |  |  | 25 | 25.21
[18 empty] | 25 | 25.21
27 | 22.4 | +0/-0.13 | DHMS |  | 0.001 | 22.34 | 22.32 | 22.36 | 22.34 | 22.35 | 22.36 | 22.34 | 22.37 | 22.33 | 22.32 |  |  | 22.27 | 22.4
[18 empty] | 22.27 | 22.4
28 | 1.5X45° | - | Video measuring system |  | 0.001 | 1: 1.5X45° PROVIDED |  |  | - | -
[18 empty] | - | -
29 | 0.8√ On face | - | Compare with measured sample |  | N/A | 1: 0.8√ MAINTAINED COMPARED WITH STD SPECIMEN |  |  | - | -
[18 empty] | - | -
30 | 14 | - | DHMS |  | 0.001 | 14.01 | 14.02 | 14.02 | 14.01 | 14.02 | 14.01 | 14.02 | 14.01 | 14.02 | 14.01 |  |  | 13.8 | 14.2
[18 empty] | 13.8 | 14.2
31 | 2 | - | Measuring pin with Video measuring system |  | 0.001 | 1.92 | 1.94 | 1.93 | 1.94 | 1.93 | 1.94 | 1.93 | 1.94 | 1.93 | 1.94 |  |  | 1.9 | 2.1
[18 empty] | 1.9 | 2.1
32 | Ø54 | +0/-0.30 | Digital vernier |  | 0.01 | 53.89 | 53.89 | 53.92 | 53.94 | 53.91 | 53.92 | 53.94 | 53.92 | 53.94 | 53.92 |  |  | 53.7 | 54
[18 empty] | 53.7 | 54
33 | 1.5@ 3-Nos | +0.25/-0 | Measuring pin 1.51 No go 1.74 |  | N/A | 1: Ø1.51 PIN GAUGE ANSWERING Ø1.74 PIN GAUGE NOT ANSWERING |  |  | 1.53 | 1.78
[18 empty] | 1.53 | 1.78
34 | Equispaced on Ø1.5 Hole | - | Measuring pin with Video measuring system |  | 0.001 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.02 | 0.03 | 0.02 |  |  | 0 | 0.1
[18 empty] | 0 | 0.1
35 | 50 | +0/-0.30 | DHMS |  | 0.001 | 49.91 | 49.93 | 49.92 | 49.93 | 49.92 | 49.94 | 49.93 | 49.94 | 49.93 | 49.92 |  |  | 49.7 | 50
[18 empty] | 49.7 | 50
36 | 33.8 | 0/-0.25 | DHMS/Video measuring system |  | 0.001 | 33.68 | 33.71 | 33.66 | 33.69 | 33.68 | 33.69 | 33.71 | 33.7 | 33.69 | 33.68 |  |  | 33.55 | 33.8
[18 empty] | 33.55 | 33.8
37 | 2.5 | - | Video measuring system |  | 0.001 | 2.51 | 2.52 | 2.51 | 2.52 | 2.51 | 2.52 | 2.51 | 2.52 | 2.51 | 2.52 |  |  | 2.4 | 2.6
[18 empty] | 2.4 | 2.6
38 | R1 *@ 2 Places | - | Radius gauge |  | N/A | 1: R1 RADIUS GAUGE MATCHED AND FOUND OK |  |  | - | -
[18 empty] | - | -
39 | 45° * | - | Video measuring system |  | 0.001 | 1: 45° PROVIDED |  |  | - | -
[18 empty] | - | -
40 | R0.5 * | - | Radius gauge |  | N/A | 1: R0.5 MAINTAINED |  |  | 0.4 | 0.6
[18 empty] | 0.4 | 0.6
41 | R2 * | - | Radius gauge |  | N/A | 1: R2 RADIUS GAUGE MATCHED AND FOUND OK |  |  | 1.9 | 2.1
[18 empty] | 1.9 | 2.1
Inspected By |  |  |  | Verified By: |  | 5: Customer Surveyor :
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
42 | Ø30 | +0.21/-0 | Bore micrometer |  | 0.001 | 30.14 | 30.12 | 30.14 | 30.11 | 30.13 | 30.12 | 30.14 | 30.12 | 30.11 | 30.12 |  |  | 30 | 30.21
[18 empty] | 30 | 30.21
43 | 3 * | - | Contour measuring system |  | 0.001 | 3.02 | 3.04 | 3.02 | 3.03 | 3.04 | 3.02 | 3.03 | 3.02 | 3.03 | 3.04 |  |  | 2.9 | 3.1
[18 empty] | 2.9 | 3.1
44 | 45° * | - | Contour measuring system |  | 0.001 | 1: 45° PROVIDED |  |  | - | -
[18 empty] | - | -
45 | R0.5 * | - | Radius gauge |  | N/A | 1: R0.5 MAINTAINED |  |  | - | -
[18 empty] | - | -
46 | R1 * | - | Radius gauge |  | N/A | 1: MEASURED BETWEEN R0.98 TO R1.03 |  |  | - | -
[18 empty] | - | -
47 | Ø42.5 | +0.250/-0 | DHMS |  | 0.001 | 42.58 | 42.64 | 42.63 | 42.64 | 42.63 | 42.62 | 42.63 | 42.66 | 42.66 | 42.65 |  |  | 42.5 | 42.75
[18 empty] | 42.5 | 42.75
48 | 0.8√ On Groove face | - | Compare with Std specimen |  | N/A | 1: 0.8√ MAINTAINED COMPARED WITH STD SPECIMEN |  |  | - | -
[18 empty] | - | -
49 | Ensure the matrial is annealed condition | - | Verify the HT report as per procedure |  | N/A | 1: MATERIAL SUPPLIED BY LPSC |  |  | - | -
[18 empty] | - | -
50 | * Dimensions to be ensured by machining tools previously inspected |  | - |  | N/A | 1: VISUALLY FOUND OK |  |  | - | -
[18 empty] | - | -
51 | ** Dimension to be ensured by machining process | - | - |  | N/A | 1: VISUALLY FOUND OK |  |  | - | -
[18 empty] | - | -
52 | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference |  |  |  | N/A | 1: REFER SUITING LIST |  |  | - | -
[18 empty] | - | -
53 | Passivation | - | Verify the report as per procedure |  | N/A | 1: TO BE DONE |  |  | - | -
[18 empty] | - | -
54 | Thread should be free from burrs end folding,chatering marks etc |  | Visual under 10X |  | N/A | 1: VISUALLY FOUND OK |  |  | - | -
[18 empty] | - | -
55 | By using TAG | - | Visual |  | N/A | 1: IDENTIFICATION TAGS ARE USED |  |  | - | -
[18 empty] | - | -
56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference |  |  |  | N/A | 1: SUITING NOT DONE. GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING |  |  | - | -
[18 empty] | - | -
57 | 3.2√ | - | - |  | - | 1: 3.2√ MAINTAINED COMPARED WITH STD SPECIMEN |  |  | - | -
[18 empty] | - | -
Inspected By |  |  |  | Verified By: |  | 5: Customer Surveyor :
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count | [14 empty] | $
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used |  | Least Count
[10 empty] | Report No. |  |  | NCR No.

## REPORT 11-25
PART NAME : INLET BELLOW END-2 |  |  | DRG.No:12CUS-6116-54-A,Rev:02,ISSUE:- |  |  |  |  | Po No :LPSC/LVF/2018E026730101 DT:12.12.2018. | [6 empty] | Report No: C-IR / 21 / 092
SL No | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.ID | Remarks/ sign | Min | Max
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
1 | 37 | +0.20/-0.20 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.02 | 37.03 | 37.02 | 37.03 | 37.02 | 37.02 |  |  | 36.8 | 37.2
[20 empty] | 36.8 | 37.2
2 | 7 | +0.20/-0 | 6.97 | 6.98 | 6.97 | 6.98 | 6.97 | 6.98 | 6.97 | 6.97 | 6.98 | 6.97 | 6.98 | 6.97 | 6.99 | 6.98 | 6.97 |  |  | 7 | 7.2
[20 empty] | 7 | 7.2
3 | ⊥ 0.03 B ** | - | 0.006 | 0.016 | 0.017 | 0.006 | 0.007 | 0.004 | 0.005 | 0.004 | 0.015 | 0.006 | 0.002 | 0.005 | 0.012 | 0.003 | 0.006 |  |  | 0 | 0.03
[20 empty] | 0 | 0.03
4 | 2 | - | 2.08 | 2.06 | 2.08 | 2.06 | 2.08 | 2.06 | 2.08 | 2.06 | 2.08 | 2.06 | 2.08 | 2.06 | 2.08 | 2.07 | 2.09 |  |  | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
5 | Ø20.4 TH *** (Left) | - | 20.468 | 19.001 | 18.982 | 18.97 | 18.951 | 18.99 | 20.524 | 18.961 | 18.996 | 18.998 | 18.953 | 18.972 | 18.99 | 19.025 | 18.987 |  |  | 20.2 | 20.6
|  |  | 20.47 | 19.002 | 18.983 | 18.973 | 18.953 | 18.991 | 20.527 | 18.964 | 19.001 | 19.003 | 18.969 | 18.974 | 18.993 | 19.027 | 18.988 |  |  | 20.2 | 20.6
5A | Ø20.4 TH *** (Right) | - | 20.472 | 18.986 | 18.959 | 18.968 | 18.949 | 18.987 | 20.543 | 18.954 | 18.972 | 18.984 | 18.945 | 18.965 | 18.986 | 19.022 | 18.982 |  |  | 20.2 | 20.6
|  |  | 20.474 | 18.987 | 18.96 | 18.97 | 18.95 | 18.989 | 20.546 | 18.958 | 18.98 | 18.989 | 18.962 | 18.968 | 18.989 | 19.024 | 18.983 |  |  | 20.2 | 20.6
6 | 0.8√ On Ø20.4 | - | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.58 | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 |  |  | 0 | 0.8
[20 empty] | 0 | 0.8
7 | Ø54 | +0.050/-0.050 | 54.02 | 54.03 | 54.02 | 54.03 | 54.02 | 54.03 | 54.02 | 54.03 | 54.02 | 54.03 | 54.02 | 54.03 | 54.02 | 54.03 | 54.02 |  |  | 53.95 | 54.05
[20 empty] | 53.95 | 54.05
8 | 48 | +0/-0.250 | 47.89 | 47.9 | 47.91 | 47.9 | 47.91 | 47.91 | 47.9 | 47.9 | 47.91 | 47.9 | 47.88 | 47.91 | 47.9 | 47.89 | 47.89 |  |  | 47.75 | 48
[20 empty] | 47.75 | 48
9 | M42X1.5-6H **** | - | 11: GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING |  |  | - | -
[20 empty] | - | -
9A | 40.376/40.676 | - | 40.59 | 40.56 | 40.56 | 40.54 | 40.56 | 40.51 | 40.62 | 40.52 | 40.54 | 40.56 | 40.54 | 40.56 | 40.54 | 40.56 | 40.54 |  |  | 40.376 | 40.676
[20 empty] | 40.376 | 40.676
10 | M42X1.5-6H | - | 0.006 | 0.012 | 0.011 | 0.006 | 0.006 | 0.005 | 0.005 | 0.004 | 0.009 | 0.008 | 0.006 | 0.006 | 0.01 | 0.007 | 0.009 |  |  | 0 | 0.03
[20 empty] | 0 | 0.03
11 | 1.5X45° | - | 11: 1.5X45° PROVIDED |  |  | - | -
[20 empty] | - | -
12 | Keep sharp on Ø54 | - | 11: KEEP SHARP PROVIDED |  |  | - | -
[20 empty] | - | -
13 | ⊚ 0.050 B ** On M42 | - | 0.004 | 0.002 | 0.006 | 0.009 | 0.008 | 0.009 | 0.004 | 0.001 | 0.02 | 0.009 | 0.012 | 0.012 | 0.006 | 0.007 | 0.005 |  |  | 0 | 0.05
[20 empty] | 0 | 0.05
14 | 15° @-2-Places | - | 11: MEASURED BETWEEN 14°56' TO 15°04' |  |  | - | -
[20 empty] | - | -
15 | 4 | - | 3.95 | 3.96 | 3.95 | 3.96 | 3.95 | 3.96 | 3.96 | 3.95 | 3.96 | 3.96 | 3.95 | 3.96 | 3.95 | 3.96 | 3.95 |  |  | 3.9 | 4.1
[20 empty] | 3.9 | 4.1
Inspected By |  |  | 13: Verified By:; 20: Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.Id | Remarks
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
16 | 1 | - | 0.99 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.99 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 |  |  | 0.9 | 1.1
[20 empty] | 0.9 | 1.1
17 | ⊥ 0.030 B On 14mm Depth Face | - | 0.016 | 0.009 | 0.01 | 0.012 | 0.004 | 0.005 | 0.013 | 0.006 | 0.021 | 0.016 | 0.003 | 0.009 | 0.01 | 0.004 | 0.007 |  |  | 0 | 0.03
[20 empty] | 0 | 0.03
18 | ⊥ 0.030 B On 11mm Depth Face | - | 0.009 | 0.003 | 0.006 | 0.008 | 0.003 | 0.004 | 0.013 | 0.004 | 0.009 | 0.01 | 0.002 | 0.002 | 0.005 | 0.001 | 0.003 |  |  | 0 | 0.03
[20 empty] | 0 | 0.03
19 | (11) | - | 11.04 | 11.06 | 11.04 | 11.06 | 11.04 | 11.06 | 11.04 | 11.06 | 11.04 | 11.06 | 11.06 | 11.04 | 11.06 | 11.05 | 11.06 |  |  | 10.8 | 11.2
[20 empty] | 10.8 | 11.2
20 | 26 | +0.10/-0.10 | 26.02 | 25.98 | 25.96 | 25.98 | 25.96 | 25.98 | 25.96 | 25.98 | 25.96 | 25.98 | 25.99 | 26.02 | 26.01 | 26.02 | 26.02 |  |  | 25.9 | 26.1
[20 empty] | 25.9 | 26.1
21 | 20 | - | 20.01 | 20 | 20.01 | 20 | 19.98 | 19.97 | 20.01 | 19.99 | 20.02 | 20.01 | 20.02 | 20.04 | 20.02 | 20.04 | 20.02 |  |  | 19.8 | 20.2
[20 empty] | 19.8 | 20.2
22 | 2 | +0.250/-0 | 2.12 | 2.14 | 2.16 | 2.16 | 2.14 | 2.16 | 2.16 | 2.14 | 2.16 | 2.14 | 2.15 | 2.14 | 2.16 | 2.14 | 2.16 |  |  | 2 | 2.25
[20 empty] | 2 | 2.25
23 | Keep sharp on Ø20.4 | - | 11: KEEP SHARP PROVIDED |  |  | - | -
[20 empty] | - | -
24 | M36X1.5-6g | - | 11: GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING |  |  | - | -
[20 empty] | - | -
24A | 35.968/35.732 | - | 35.9 | 35.88 | 35.89 | 35.9 | 35.89 | 35.9 | 35.89 | 35.9 | 35.89 | 35.9 | 35.89 | 35.9 | 35.88 | 35.87 | 35.88 |  |  | 34 | 38
[20 empty] | 34 | 38
25 | ⊚Ø 0.050 B ** On M36 | - | 0.017 | 0.002 | 0.004 | 0.006 | 0.003 | 0.002 | 0.017 | 0.002 | 0.006 | 0.006 | 0.008 | 0.003 | 0.005 | 0.002 | 0.001 |  |  | 0 | 0.05
[20 empty] | 0 | 0.05
26 | Ø25 | +0.21/-0 | 25.13 | 25.12 | 25.14 | 25.13 | 25.13 | 25.12 | 25.13 | 25.12 | 25.12 | 25.13 | 25.12 | 25.14 | 25.12 | 25.13 | 25.14 |  |  | 25 | 25.21
[20 empty] | 25 | 25.21
27 | Ø22.4 | +0/-0.13 | 22.34 | 22.36 | 22.34 | 22.32 | 22.3 | 22.32 | 22.34 | 22.32 | 22.34 | 22.36 | 22.34 | 22.36 | 22.34 | 22.36 | 22.34 |  |  | 22.27 | 22.4
[20 empty] | 22.27 | 22.4
28 | 1.5X45° | - | 11: 1.5X45° PROVIDED |  |  | - | -
[20 empty] | - | -
29 | 0.8√ On face | - | 11: 0.8√ MAINTAINED COMPARED WITH STD SPECIMEN |  |  | - | -
[20 empty] | - | -
30 | 14 | - | 14.02 | 14.01 | 14.02 | 14.01 | 14.02 | 14.01 | 14.02 | 14.01 | 14.04 | 14.02 | 14.03 | 14.02 | 14.03 | 14.02 | 14.02 |  |  | 13.8 | 14.2
[20 empty] | 13.8 | 14.2
Inspected By |  |  | 13: Verified By:; 20: Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.Id | Remarks
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
31 | 2 | - | 1.92 | 1.94 | 1.96 | 1.92 | 1.95 | 1.96 | 1.94 | 1.96 | 1.96 | 1.94 | 1.92 | 1.94 | 1.94 | 1.96 | 1.94 |  |  | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
32 | Ø54 | +0/-0.30 | 53.89 | 53.86 | 53.89 | 53.86 | 53.89 | 53.88 | 53.89 | 53.89 | 53.89 | 53.91 | 53.92 | 53.92 | 53.92 | 53.94 | 53.92 |  |  | 53.7 | 54
[20 empty] | 53.7 | 54
33 | Ø1.5@ 3-Nos | +0.25/-0 | 11: Ø1.51 PIN GAUGE ANSWERING Ø1.74 PIN GAUGE NOT ANSWERING |  |  | 1.53 | 1.78
[20 empty] | 1.53 | 1.78
34 | Equispaced on Ø1.5 Hole | - | 0.02 | 0.03 | 0.02 | 0.03 | 0.04 | 0.02 | 0.03 | 0.03 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.02 |  |  | 0 | 0.1
[20 empty] | 0 | 0.1
35 | 50 | +0/-0.30 | 49.92 | 49.91 | 49.9 | 49.91 | 49.92 | 49.91 | 49.9 | 49.89 | 49.91 | 49.92 | 49.9 | 49.9 | 49.88 | 49.89 | 49.87 |  |  | 49.7 | 50
[20 empty] | 49.7 | 50
36 | Ø33.8 | 0/-0.25 | 33.69 | 33.71 | 33.72 | 33.69 | 33.69 | 33.7 | 33.69 | 33.68 | 33.71 | 33.7 | 33.69 | 33.7 | 33.69 | 33.68 | 33.69 |  |  | 33.55 | 33.8
[20 empty] | 33.55 | 33.8
37 | 2.5 | - | 2.51 | 2.52 | 2.51 | 2.5 | 2.51 | 2.5 | 2.52 | 2.51 | 2.5 | 2.52 | 2.49 | 2.52 | 2.51 | 2.52 | 2.51 |  |  | 2.4 | 2.6
[20 empty] | 2.4 | 2.6
38 | R1 *@ 2 Places | - | 11: R1 RADIUS GAUGE MATCHED AND FOUND OK |  |  | - | -
[20 empty] | - | -
39 | 45° * | - | 11: 45° PROVIDED |  |  | - | -
[20 empty] | - | -
40 | R0.5 * | - | 11: R0.5 MAINTAINED |  |  | 0.4 | 0.6
[20 empty] | 0.4 | 0.6
41 | R2 * | - | 11: R2 RADIUS GAUGE MATCHED AND FOUND OK |  |  | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
42 | Ø30 | +0.21/-0 | 30.14 | 30.12 | 30.14 | 30.16 | 30.14 | 30.12 | 30.13 | 30.13 | 30.14 | 30.13 | 30.12 | 30.12 | 30.14 | 30.12 | 30.13 |  |  | 30 | 30.21
[20 empty] | 30 | 30.21
43 | 3 * | - | 3.02 | 3.04 | 3.02 | 3.02 | 3.04 | 3.02 | 3.03 | 3.02 | 3.03 | 3.04 | 3.03 | 3.04 | 3.02 | 3.03 | 3.04 |  |  | 2.9 | 3.1
[20 empty] | 2.9 | 3.1
44 | 45° * | - | 11: 45° PROVIDED |  |  | - | -
[20 empty] | - | -
45 | R0.5 * | - | 11: R0.5 MAINTAINED |  |  | - | -
[20 empty] | - | -
46 | R1 * | - | 11: MEASURED BETWEEN R0.98 TO R1.03 |  |  | - | -
[20 empty] | - | -
Inspected By |  |  | 13: Verified By:; 20: Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | Inst.Id | Remarks
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
47 | Ø42.5 | +0.250/-0 | 42.58 | 42.56 | 42.59 | 42.58 | 42.56 | 42.58 | 42.56 | 42.58 | 42.58 | 42.56 | 42.58 | 42.56 | 42.58 | 42.59 | 42.58 |  |  | 42.5 | 42.75
[20 empty] | 42.5 | 42.75
48 | 0.8√ On Groove face | - | 11: 0.8√ MAINTAINED COMPARED WITH STD SPECIMEN |  |  | - | -
[20 empty] | - | -
49 | Ensure the matrial is annealed condition | - | 11: MATERIAL SUPPLIED BY LPSC |  |  | - | -
[20 empty] | - | -
50 | * Dimensions to be ensured by machining tools previously inspected |  | 11: VISUALLY FOUND OK |  |  | - | -
[20 empty] | - | -
51 | ** Dimension to be ensured by machining process |  | 11: VISUALLY FOUND OK |  |  | - | -
[20 empty] | - | -
52 | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference |  | 11: REFER SUITING LIST |  |  | - | -
[20 empty] | - | -
53 | Passivation | - | 11: TO BE DONE |  |  | - | -
[20 empty] | - | -
54 | Thread should be free from burrs end folding,chatering marks etc |  | 11: VISUALLY FOUND OK |  |  | - | -
[20 empty] | - | -
55 | By using TAG | - | 11: IDENTIFICATION TAGS ARE USED |  |  | - | -
[20 empty] | - | -
56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference |  | 11: SUITING NOT DONE. GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING |  |  | - | -
[20 empty] | - | -
57 | 3.2√ | - | 11: 3.2√ MAINTAINED COMPARED WITH STD SPECIMEN |  |  | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 13: Verified By:; 20: Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
1 | 37 | +0.20/-0.20 | 37.01 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.01 | 37.02 | 37.01 | [8 empty] | 36.8 | 37.2
[20 empty] | 36.8 | 37.2
2 | 7 | +0.20/-0 | 6.97 | 6.98 | 6.97 | 6.96 | 6.97 | 6.96 | 6.97 | 6.96 | 6.97 | [8 empty] | 7 | 7.2
[20 empty] | 7 | 7.2
3 | ⊥ 0.03 B ** | - | 0.021 | 0.01 | 0.021 | 0.03 | 0.007 | 0.009 | 0.003 | 0.007 | 0.005 | [8 empty] | 0 | 0.03
[20 empty] | 0 | 0.03
4 | 2 | - | 2.07 | 2.08 | 2.07 | 2.08 | 2.08 | 2.07 | 2.08 | 2.07 | 2.08 | [8 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
5 | Ø20.4 TH *** (Left) | - | 18.946 | 18.955 | 18.955 | 19.002 | 18.987 | 18.98 | 18.96 | 19.004 | 18.981 | [8 empty] | 20.2 | 20.6
|  |  | 18.948 | 18.956 | 18.958 | 19.006 | 18.988 | 18.982 | 18.963 | 19.005 | 18.984 | [8 empty] | 20.2 | 20.6
5A | Ø20.4 TH *** (Right) | - | 18.935 | 18.958 | 18.947 | 18.987 | 18.975 | 18.973 | 18.953 | 18.976 | 18.975 | [8 empty] | 20.2 | 20.6
|  |  | 18.937 | 18.959 | 18.95 | 18.992 | 18.976 | 18.975 | 18.954 | 18.978 | 18.972 | [8 empty] | 20.2 | 20.6
6 | 0.8√ On Ø20.4 | - | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 | 0.58 | 0.56 | 0.56 | 0.58 | [8 empty] | 0 | 0.8
[20 empty] | 0 | 0.8
7 | Ø54 | +0.050/-0.050 | 54.01 | 54.02 | 54.01 | 54.01 | 54.02 | 54.01 | 54.02 | 54.01 | 54.02 | [8 empty] | 53.95 | 54.05
[20 empty] | 53.95 | 54.05
8 | 48 | +0/-0.250 | 47.9 | 47.91 | 47.9 | 47.91 | 47.84 | 47.9 | 47.9 | 47.88 | 47.89 | [8 empty] | 47.75 | 48
[20 empty] | 47.75 | 48
9 | M42X1.5-6H **** | - | 26: GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING | [8 empty] | - | -
[20 empty] | - | -
9A | 40.376/40.676 | - | 40.54 | 40.56 | 40.54 | 40.56 | 40.55 | 40.56 | 40.54 | 40.56 | 40.54 | [8 empty] | 40.376 | 40.676
[20 empty] | 40.376 | 40.676
10 | ⊥ 0.03 B | - | 0.015 | 0.009 | 0.014 | 0.02 | 0.006 | 0.007 | 0.003 | 0.008 | 0.006 | [8 empty] | 0 | 0.03
[20 empty] | 0 | 0.03
11 | 1.5X45° | - | 26: 1.5X45° PROVIDED | [8 empty] | - | -
[20 empty] | - | -
12 | Keep sharp on Ø54 | - | 26: KEEP SHARP PROVIDED | [8 empty] | - | -
[20 empty] | - | -
13 | ⊚ 0.050 B ** On M42 | - | 0.017 | 0.008 | 0.011 | 0.013 | 0.003 | 0.018 | 0.013 | 0.014 | 0.006 | [8 empty] | 0 | 0.05
[20 empty] | 0 | 0.05
14 | 15° @-2-Places | - | 26: MEASURED BETWEEN 14°56' TO 15°04' | [8 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 28: Verified By: | Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
15 | 4 | - | 3.95 | 3.96 | 3.97 | 3.96 | 3.95 | 3.96 | 3.95 | 3.95 | 3.96 | [8 empty] | 3.9 | 4.1
[20 empty] | 3.9 | 4.1
16 | 1 | - | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 | 0.98 | 0.96 | [8 empty] | 0.9 | 1.1
[20 empty] | 0.9 | 1.1
17 | ⊥ 0.030 B On 14mm Depth Face | - | 0.006 | 0.005 | 0.009 | 0.018 | 0.011 | 0.008 | 0.008 | 0.014 | 0.017 | [8 empty] | 0 | 0.03
[20 empty] | 0 | 0.03
18 | ⊥ 0.030 B On 11mm Depth Face | - | 0.005 | 0.004 | 0.003 | 0.007 | 0.005 | 0.002 | 0.003 | 0.005 | 0.008 | [8 empty] | 0 | 0.03
[20 empty] | 0 | 0.03
19 | (11) | - | 11.06 | 11.05 | 11.05 | 11.06 | 11.05 | 11.06 | 11.05 | 11.06 | 11.05 | [8 empty] | 10.8 | 11.2
[20 empty] | 10.8 | 11.2
20 | 26 | +0.10/-0.10 | 26.02 | 26.01 | 26.01 | 26.02 | 26.01 | 26.02 | 26.01 | 26.02 | 26.01 | [8 empty] | 25.9 | 26.1
[20 empty] | 25.9 | 26.1
21 | 20 | - | 20.04 | 20.04 | 20.02 | 20.04 | 20.02 | 20.04 | 20.02 | 20.04 | 20.02 | [8 empty] | 19.8 | 20.2
[20 empty] | 19.8 | 20.2
22 | 2 | +0.250/-0 | 2.15 | 2.14 | 2.15 | 2.14 | 2.15 | 2.14 | 2.15 | 2.14 | 2.15 | [8 empty] | 2 | 2.25
[20 empty] | 2 | 2.25
23 | Keep sharp on Ø20.4 | - | 26: KEEP SHARP PROVIDED | [8 empty] | - | -
[20 empty] | - | -
24 | M36X1.5-6g | - | 26: GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING | [8 empty] | - | -
[20 empty] | - | -
24A | 35.968/35.732 | - | 35.98 | 35.97 | 35.96 | 35.97 | 35.96 | 35.98 | 35.97 | 35.96 | 35.97 | [8 empty] | 34 | 38
[20 empty] | 34 | 38
25 | ⊚Ø 0.050 B ** On M36 | - | 0.001 | 0.004 | 0.002 | 0.005 | 0.004 | 0.001 | 0.002 | 0.005 | 0.006 | [8 empty] | 0 | 0.05
[20 empty] | 0 | 0.05
26 | Ø25 | +0.21/-0 | 25.11 | 25.12 | 25.14 | 25.14 | 25.12 | 25.12 | 25.14 | 25.12 | 25.14 | [8 empty] | 25 | 25.21
[20 empty] | 25 | 25.21
27 | Ø22.4 | +0/-0.13 | 22.34 | 22.36 | 22.34 | 22.36 | 22.34 | 22.36 | 22.34 | 22.36 | 22.34 | [8 empty] | 22.27 | 22.4
[20 empty] | 22.27 | 22.4
28 | 1.5X45° | - | 26: 1.5X45° PROVIDED | [8 empty] | - | -
[20 empty] | - | -
29 | 0.8√ On face | - | 26: 0.8√ MAINTAINED COMPARED WITH STD SPECIMEN | [8 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 28: Verified By: | Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
30 | 14 | - | 14.01 | 14.02 | 14.01 | 14.02 | 14.01 | 14.01 | 14.01 | 14.01 | 14.02 | [8 empty] | 13.8 | 14.2
[20 empty] | 13.8 | 14.2
31 | 2 | - | 1.92 | 1.94 | 1.94 | 1.92 | 1.94 | 1.93 | 1.92 | 1.94 | 1.92 | [8 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
32 | Ø54 | +0/-0.30 | 53.92 | 53.94 | 53.92 | 53.94 | 53.92 | 53.94 | 53.94 | 53.92 | 53.94 | [8 empty] | 53.7 | 54
[20 empty] | 53.7 | 54
33 | Ø1.5@ 3-Nos | +0.25/-0 | 26: Ø1.51 PIN GAUGE ANSWERING Ø1.74 PIN GAUGE NOT ANSWERING | [8 empty] | 1.53 | 1.78
[20 empty] | 1.53 | 1.78
34 | Equispaced on Ø1.5 Hole | - | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | [8 empty] | 0 | 0.1
[20 empty] | 0 | 0.1
35 | 50 | +0/-0.30 | 49.92 | 49.94 | 49.93 | 49.94 | 49.93 | 49.94 | 49.95 | 49.94 | 49.96 | [8 empty] | 49.7 | 50
[20 empty] | 49.7 | 50
36 | Ø33.8 | 0/-0.25 | 33.68 | 33.66 | 33.68 | 33.66 | 33.68 | 33.66 | 33.68 | 33.67 | 33.68 | [8 empty] | 33.55 | 33.8
[20 empty] | 33.55 | 33.8
37 | 2.5 | - | 2.51 | 2.44 | 2.52 | 2.54 | 2.52 | 2.54 | 2.52 | 2.54 | 2.52 | [8 empty] | 2.4 | 2.6
[20 empty] | 2.4 | 2.6
38 | R1 *@ 2 Places | - | 26: R1 RADIUS GAUGE MATCHED AND FOUND OK | [8 empty] | - | -
[20 empty] | - | -
39 | 45° * | - | 26: 45° PROVIDED | [8 empty] | - | -
[20 empty] | - | -
40 | R0.5 * | - | 26: R0.5 MAINTAINED | [8 empty] | 0.4 | 0.6
[20 empty] | 0.4 | 0.6
41 | R2 * | - | 26: R2 RADIUS GAUGE MATCHED AND FOUND OK | [8 empty] | 1.9 | 2.1
[20 empty] | 1.9 | 2.1
42 | Ø30 | +0.21/-0 | 30.12 | 30.11 | 30.13 | 30.12 | 30.13 | 30.12 | 30.13 | 30.02 | 30.04 | [8 empty] | 30 | 30.21
[20 empty] | 30 | 30.21
43 | 3 * | - | 3.02 | 3.03 | 3.02 | 3.04 | 3.03 | 3.04 | 3.05 | 3.06 | 3.08 | [8 empty] | 2.9 | 3.1
[20 empty] | 2.9 | 3.1
44 | 45° * | - | 26: 45° PROVIDED | [8 empty] | - | -
[20 empty] | - | -
45 | R0.5 * | - | 26: R0.5 MAINTAINED | [8 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 28: Verified By: | Customer Surveyor :
slno | Specification in MM | Tol. | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | LA849 | [6 empty] | Inst.Id | Remarks
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
46 | R1 * | - | 26: MEASURED BETWEEN R0.98 TO R1.03 | [8 empty] | - | -
[20 empty] | - | -
47 | Ø42.5 | +0.250/-0 | 42.58 | 42.56 | 42.58 | 42.58 | 42.56 | 42.56 | 42.58 | 42.56 | 42.58 | [8 empty] | 42.5 | 42.75
[20 empty] | 42.5 | 42.75
48 | 0.8√ On Groove face | - | 26: 0.8√ MAINTAINED COMPARED WITH STD SPECIMEN | [8 empty] | - | -
[20 empty] | - | -
49 | Ensure the matrial is annealed condition | - | 26: MATERIAL SUUPPLIED BY LPSC | [8 empty] | - | -
[20 empty] | - | -
50 | * Dimensions to be ensured by machining tools previously inspected |  | 26: VISUALLY FOUND OK | [8 empty] | - | -
[20 empty] | - | -
51 | ** Dimension to be ensured by machining process |  | 26: VISUALLY FOUND OK | [8 empty] | - | -
[20 empty] | - | -
52 | *** To be suited to given bellow with 5 to 10 microns interference fit identify the pair for future reference |  | 26: REFER SUITING LIST | [8 empty] | - | -
[20 empty] | - | -
53 | Passivation | - | 26: TO BE DONE | [8 empty] | - | -
[20 empty] | - | -
54 | Thread should be free from burrs end folding,chatering marks etc |  | 26: VISUALLY FOUND OK | [8 empty] | - | -
[20 empty] | - | -
55 | By using TAG | - | 26: IDENTIFICATION TAGS ARE USED | [8 empty] | - | -
[20 empty] | - | -
56 | *** Suit the thread with corresponding thread of main body sub assy (Drg No 12cus-6116-70-00 sht1-2)identify the pair for future reference |  | 26: SUITING NOT DONE. GO GAUGE ANSWERING NO GO GAUGE NOT ANSWERING | [8 empty] | - | -
[20 empty] | - | -
57 | 3.2√ | - | 26: 3.2√ MAINTAINED COMPARED WITH STD SPECIMEN | [8 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
[20 empty] | - | -
Inspected By |  |  | 28: Verified By: | Customer Surveyor :
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor
slno | Specification in MM | Tol. | [15 empty] | Inst.Id | Remarks
Inspected By |  |  | 27: Verified By:; 33: Customer sueveyor

## Aft ST
CHAKRADHARA AEROSPACE AND CARGO PRIVATE LIMITED QUALITY CONTROL DEPARTMENT | [12 empty] | L
INSPECTION REPORT | [7 empty] | WO No : 2010521 | Wo No:2010521
PROJECT : LTIV.OHPR & UTIV PARTS |  |  | PART NAME : INLET BELLOW END-2 |  |  |  | DRG.No: 12CUS-6116-54-A,Rev:02,ISSUE:- |  | FIR No:
Po No : LPSC/LVF/2018E026730101 DT:12.12.2018. |  |  | ASSY NAME : - |  | MATL. SPEC : SS 12X18 H10T |  | Stage: AFTER PASSIVATION | Report No: C-IR / 21 / 348 | Date:
Offered Qty :34No's |  |  | PART ID NO's : LA8491 To LA84934 |  | RMC NO: XSR/1030-46 |  | Matl Used: AISI 321 (SS 12X18H10T) | NCR NO: ─ | B.Qty:
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count |  |  |  |  | Inst.ID: | Remarks | Min | Max
1 | Visual |  |  |  | VISUALLY SEEN FOUND OK | [5 empty] | 36.8 | 37.2
[11 empty] | 36.8 | 37.2
CACPL | [5 empty] | CUSTOMER SURVEYOR
Inspected By: P. KUMAR |  |  | Sign & Stamp |  |  | Qty Accepted | Qty Concession | Qty Rejected
Verified By: M. SARAVANAN |  |  | Sign & Stamp |  |  | Name & Signature :
DATE: 30.01.2021. |  |  | DATE: |  |  | Date :
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.
SLNO | Specification in MM | Tol. | Instruments / Gauges used | Least Count
[7 empty] | Report No. | NCR No.

## NCR
CHAKRADHARA AEROSPACE AND CARGO PRIVATE LIMITED QUALITY CONTROL DEPARTMENT
|  | NON CONFORMITY REPORT | [6 empty] | Work Centre : CACPL
PROJECT : LTIV.OHPR & UTIV PARTS |  |  |  | PART NAME : INLET BELLOW END-2 |  |  |  | DRG.No: 12CUS-6116-54-A,Rev:02,ISSUE:-
Po No : LPSC/LVF/2018E026730101 DT:12.12.2018. | [6 empty] | ASSY NAME : - | MATL. SPEC : SS 12X18 H10T |  | Stage: BEFORE PASSIVATION | NCR NO: C-NC / 21 / 033
Offered Qty :34No's |  |  | Ncr Qty::34No's |  |  |  |  | RMC NO: XSR/1030-46 |  | Matl Used: AISI 321 (SS 12X18H10T) | Report No: C-IR / 21 / 092
Sl. No | Dim sl. no. | Specification in MM |  |  | Tol. | DRG. ZONE
Prepared By : | [8 empty] | Verified By :
Sl. No | Dim sl. no. | Specification in MM |  |  | Tol. | DRG. ZONE
Prepared By : | [8 empty] | Verified By :